## Agile Sprint Roadmap
AGILE SPRINT BACKLOG, STORY POINTS, VELOCITY & PRODUCT LAUNCH ROADMAP
Engineering & Product Release Tracker with Sprint Capacity, Completion % & Risk Flags
TOTAL STORY POINTS |  |  | COMPLETED POINTS (VELOCITY) |  |  | OVERALL COMPLETION % |  |  | COMPLETED EPICS/STORIES |  | TOTAL EST. ENG HOURS
Story ID | Epic / Workstream | User Story / Deliverable | Sprint | Owner | Story Points | Points Completed | Completion % | Est. Hours | Actual Hours | Status | Priority | Delivery Health
US-201 | Auth & SSO | OAuth2 + SAML Enterprise Login Flow | Sprint 14 | A. Bahloul | 8 | 8 |  |  | 34 |  | P0 - Critical
US-202 | Auth & SSO | Role-Based Access Control (RBAC) Matrix | Sprint 14 | S. Chen | 5 | 5 |  |  | 22 |  | P0 - Critical
US-203 | Billing Engine | Stripe Subscription & Usage Metering Webhook | Sprint 14 | M. Alvarez | 13 | 13 |  |  | 52 |  | P0 - Critical
US-204 | Billing Engine | Self-Serve Plan Upgrade & Proration UI | Sprint 15 | M. Alvarez | 8 | 8 |  |  | 30 |  | P1 - High
US-205 | AI Copilot | Vector Embeddings Pipeline & RAG Indexing | Sprint 15 | D. Kumar | 13 | 10 |  |  | 48 |  | P0 - Critical
US-206 | AI Copilot | Streaming Prompt Response UI with Citations | Sprint 15 | L. Novak | 8 | 6 |  |  | 29 |  | P1 - High
US-207 | Analytics Hub | Executive Cohort Retention & LTV Charting | Sprint 16 | S. Chen | 8 | 5 |  |  | 26 |  | P1 - High
US-208 | Analytics Hub | Scheduled CSV/PDF Report Email Dispatcher | Sprint 16 | K. Patel | 5 | 5 |  |  | 19 |  | P2 - Medium
US-209 | Mobile App | React Native Offline Sync & Local Cache | Sprint 16 | J. Rossi | 13 | 7 |  |  | 45 |  | P1 - High
US-210 | Mobile App | Biometric FaceID Passkey Quick Unlock | Sprint 17 | J. Rossi | 5 | 2 |  |  | 14 |  | P2 - Medium
US-211 | Integrations | Bi-Directional HubSpot & Salesforce CRM Sync | Sprint 17 | A. Bahloul | 13 | 4 |  |  | 38 |  | P1 - High
US-212 | Integrations | Slack & Microsoft Teams Alert Bot | Sprint 17 | K. Patel | 5 | 0 |  |  | 8 |  | P2 - Medium
US-213 | Performance | Postgres Read-Replica & Redis Query Caching | Sprint 18 | D. Kumar | 8 | 0 |  |  | 12 |  | P1 - High
US-214 | Security & SOC2 | Automated Audit Trail & Penetration Fixes | Sprint 18 | A. Bahloul | 8 | 8 |  |  | 31 |  | P0 - Critical
US-215 | Launch Ops | Public API v2 Documentation & SDK Release | Sprint 18 | L. Novak | 5 | 3 |  |  | 16 |  | P1 - High
ROADMAP TOTALS