## Dashboard & Model
GO-TO-MARKET (GTM) PRODUCT LAUNCH MASTER MILESTONE ROADMAP
BizTools Executive Financial & Operations Engine • Automated Dynamic Formulas
Total Launch Tasks |  | Completed Deliverables |  | Launch Progress % |  | Budget Expended
Launch Phase | Milestone / Deliverable | Owner | Due Date | Est. Budget | Actual Cost | Execution Status | Priority
Phase 1: Discovery | Competitive Pricing & Positioning Matrix | Product Lead | 2026-11-01 | 3500 | 3200 | Completed | High
Phase 1: Discovery | User Persona & Jobs-To-Be-Done Map | UX Lead | 2026-11-05 | 4000 | 4100 | Completed | High
Phase 2: Validation | High-Converting Landing Page Design | Design Lead | 2026-11-12 | 6500 | 6200 | Completed | High
Phase 2: Validation | Waitlist Email Sequence & Lead Magnet | Copywriter | 2026-11-18 | 2500 | 2400 | Completed | Medium
Phase 3: Production | Core MVP Feature Freeze & QA Audit | Tech Lead | 2026-11-25 | 12000 | 11800 | Completed | Critical
Phase 3: Production | Stripe & PayPal Checkout Integration | Backend Dev | 2026-11-28 | 3000 | 3000 | Completed | Critical
Phase 4: Marketing | Product Hunt Pre-Launch & Teaser Page | Growth Lead | 2026-12-02 | 1500 | 1400 | In Progress | High
Phase 4: Marketing | Influencer Seed Kit & Demo Outreach | PR Specialist | 2026-12-05 | 4500 | 4800 | In Progress | Medium
Phase 4: Marketing | Paid Meta & Google Search Ad Creatives | Media Buyer | 2026-12-08 | 5000 | 4600 | In Progress | High
Phase 5: Launch Day | Product Hunt Launch & Community Blitz | Founder / CEO | 2026-12-12 | 2000 | 1500 | Scheduled | Critical
Phase 5: Launch Day | Live Demo Webinar & Q&A Stream | Growth Lead | 2026-12-12 | 1000 | 800 | Scheduled | High
Phase 6: Retention | Onboarding Email Drip Automation | Lifecycle Lead | 2026-12-16 | 2000 | 1900 | Scheduled | High
Phase 6: Retention | Referral & Affiliate Program Activation | Partnerships | 2026-12-20 | 3500 | 3100 | Scheduled | Medium
Phase 6: Retention | Customer CSAT Survey & Feature Voting | Product Lead | 2026-12-28 | 1500 | 1200 | Scheduled | Low
GTM TOTAL | [5 empty] | 92% On-Schedule