## Renovation Budget & Variance
HOME REMODEL & CONSTRUCTION ROOM-BY-ROOM LABOR, MATERIALS & VARIANCE TRACKER
Contractor Trade Estimates, 10% Contingency Reserve, Actual Spend & Budget Variance Control
TOTAL APPROVED BUDGET |  |  | TOTAL ACTUAL SPEND TO DATE |  |  | TOTAL CONTINGENCY RESERVE |  |  | NET BUDGET VARIANCE ($) |  | SCOPES UNDER/ON BUDGET
Scope ID | Room / Zone | Trade & Work Package | Contractor / Vendor | Materials Est ($) | Labor Est ($) | Contingency (10%) | Total Approved Budget ($) | Actual Spend ($) | Variance ($ Saved/Over) | Variance % | Completion Stage | Budget Status
RNV-01 | Site & Demo | Architectural Plans, Permits & Interior Demo | Apex Structural | 3200 | 6800 |  |  | 10400 |  |  | 100% Complete
RNV-02 | Chef Kitchen | Custom White Oak Cabinetry & Soft-Close Millwork | Nordic Millworks | 16500 | 7200 |  |  | 25400 |  |  | 100% Complete
RNV-03 | Chef Kitchen | Calacatta Quartz Countertops & Waterfall Island | StoneCraft Lab | 7800 | 3400 |  |  | 11900 |  |  | 100% Complete
RNV-04 | Chef Kitchen | Pro-Grade Induction Range, Hood & Panel Fridge | Luxe Appliances | 12400 | 1800 |  |  | 14800 |  |  | 100% Complete
RNV-05 | Primary Suite Bath | Frameless Glass Wet-Room, Freestanding Tub & Tile | Oasis Bath Co. | 8900 | 9400 |  |  | 19600 |  |  | 90% In Progress
RNV-06 | Primary Suite Bath | Floating Double Vanity, Brushed Brass Fixtures | Oasis Bath Co. | 4600 | 2900 |  |  | 8100 |  |  | 100% Complete
RNV-07 | Whole House Flooring | Wide-Plank European White Oak Hardwood & Leveling | Timberline Floors | 11200 | 6800 |  |  | 19200 |  |  | 100% Complete
RNV-08 | Electrical & Lighting | 200A Panel Upgrade, Recessed LEDs & Smart Dimmers | VoltMaster Electric | 4800 | 7500 |  |  | 13400 |  |  | 100% Complete
RNV-09 | Plumbing & MEP | PEX Repipe, Tankless Water Heater & Rough-Ins | ClearFlow Plumbing | 4200 | 6400 |  |  | 11800 |  |  | 100% Complete
RNV-10 | HVAC & Climate | High-Efficiency Heat Pump & Smart Zoning Ductwork | AeroClimate Systems | 7900 | 5600 |  |  | 14500 |  |  | 80% In Progress
RNV-11 | Living & Dining | Drywall Skim Coat, Acoustic Insulation & Paint | Precision Finishes | 2900 | 6200 |  |  | 9600 |  |  | 75% In Progress
RNV-12 | Windows & Doors | Low-E Black Aluminum Casement Windows & Bi-Fold | Vista Glazing | 13500 | 5200 |  |  | 20100 |  |  | 100% Complete
RNV-13 | Guest Powder Room | Herringbone Mosaic Wall, Pedestal Sink & Sconces | Oasis Bath Co. | 2600 | 2800 |  |  | 5800 |  |  | 60% In Progress
RNV-14 | Exterior & Deck | Composite Cedar Decking, Pergola & Landscape LED | Evergreen Outdoor | 8400 | 6100 |  |  | 15200 |  |  | 40% In Progress
PROJECT TOTALS | [10 empty] | ACTIVE REMODEL